## Dashboard
PREMIER FINISH & CONSTRUCTION · PROJECT MASTER TRACKER
[Building Name / Address]
PROGRESS SUMMARY (units, out of 36)
Phase | Not Started | In Progress | Complete | Deficiency | On Hold
Phase 1 — Doors & Windows | 36 | 0 | 0 | 0 | 0
Phase 2 — Baseboards | 36 | 0 | 0 | 0 | 0
Phase 3 — Hardware | 36 | 0 | 0 | 0 | 0
Other | 36 | 0 | 0 | 0 | 0
UNIT OVERALL STATUS (whole-unit rollup)
Status | Not Started | In Progress | Complete | Deficiency | On Hold
Count | 36 | 0 | 0 | 0 | 0

## Unit Tracker
PREMIER FINISH & CONSTRUCTION · MASTER TRACKER TEMPLATE
[Building Name / Address] · [Total Units]
LOCATION |  | PHASE 1 · DOORS & WINDOWS | [11 empty] | PHASE 2 · BASEBOARDS |  |  |  | PHASE 3 · HARDWARE & ACCESSORIES | [19 empty] | OTHER |  | PHASE ROLLUP |  |  |  | PROGRESS
|  | INTERIOR DOORS |  | UNIT DOOR |  | PATIO DOOR(S) |  | WINDOWS |  | ATTIC HATCH |  | HANDRAIL |  | CUT |  | NAILED |  | PASSAGE |  | PRIVACY |  | DUMMY |  | DEADBOLT |  | BALL CATCH |  | SPRING STOP |  | HINGE STOP |  | MIRROR |  | BATHROOM ACCESSORY |  | FIRESWEEP / PEEPHOLE / SPRING |  | OTHER (CUSTOM ITEM) |  | PHASE 1 | PHASE 2 | PHASE 3 | OTHER | DATE | COMPLETION
Floor | Unit # | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Details | Status | Status | Status | Status | LAST UPDATED | OVERALL STATUS
1 | 101 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 102 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 103 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 104 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 105 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 106 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 107 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 108 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 109 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 110 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 111 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
1 | 112 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 201 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 202 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 203 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 204 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 205 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 206 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 207 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 208 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 209 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 210 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 211 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
2 | 212 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 301 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 302 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 303 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 304 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 305 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 306 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 307 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 308 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 309 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 310 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 311 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started
3 | 312 | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Not Started | Not Started | Not Started |  | Not Started